## Sheet1
☑ = milestone D = deliverable | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Initial plan | Week 1: ☑ D
Background reading | bar: Week 2
Implementation - Research | bar: Week 2 to Week 3
Implementation - Preprocessing | Week 4: ☑ ☑ D
Implementation - Clustering | Week 5: ☑; Week 6: ☑ D
Implementation - Visualisation | bar: Week 6 to Week 8
Implementation - Correlation | Week 8: ☑ D
Testing | bar: Week 9
Analysis | bar: Week 9 to Week 10
Report | Week 12: ☑ D